## Projected
|  | 22nd Feb | 1st Mar | 8th Mar | 15th Mar | 22nd Mar | 29th Mar | 6th April | 12th Apr | 19th Apr | 26th Apr | 3rd May | 10th May | 17th May | 24th May | 31st May
WP | Task | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15
Report
Create an account | bar: Wk1
Load template | bar: Wk1
Read guidelines | bar: Wk1
Deliverables
Create GIT Account | bar: Wk2
Share with lecturer | bar: Wk2
Commit regularly | bar: Wk3 to Wk15
Record prototype | bar: Wk14
Upload VIVA | bar: Wk14
Submit report | bar: Wk14
Research Methodology
Hypothesis | bar: Wk3 to Wk4
Research Questions | bar: Wk3 to Wk4
Research Methods | bar: Wk4 to Wk7
Research Pipeline | bar: Wk5 to Wk8
Finalise section in report | bar: Wk13 to Wk14
Literature Review
Review datasets | bar: Wk5 to Wk7
Review algorithms | bar: Wk5 to Wk7
Review evaluation metrics | bar: Wk5 to Wk7
Finalise section in report | bar: Wk8 to Wk9
Prototype
Tutorial / Training | bar: Wk2 to Wk9
Setup Environment / Code | bar: Wk3 to Wk9
Create custom dataset | bar: Wk6 to Wk11
Tweek prototype | bar: Wk10 to Wk11
Generate evaluation results | bar: Wk11 to Wk12
Discussion of Results
Write prototype evaluation | bar: Wk12 to Wk13
Write dataset evaluation | bar: Wk12 to Wk13
Write hypothesis testing | bar: Wk13 to Wk14
Write project evaluation | bar: Wk13 to Wk14
Finalise section in report | bar: Wk13 to Wk14
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations | bar: Wk14
Finalise Introduction | bar: Wk14
Finalise Abstract | bar: Wk14

## Actual
|  | 22nd Feb | 1st Mar | 8th Mar | 15th Mar | 22nd Mar | 29th Mar | 6th April | 12th Apr | 19th Apr | 26th Apr | 3rd May | 10th May | 17th May | 24th May | 31st May
WP | Task | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15
Report
Create an account | bar: Wk1 to Wk2
Load template | bar: Wk1 to Wk2
Read guidelines | bar: Wk1 to Wk2
Deliverables
Create GIT Account | bar: Wk2
Share with lecturer | bar: Wk2
Commit regularly | bar: Wk3 to WK8
Record prototype
Upload VIVA
Submit report
Research Methodology
Hypothesis | bar: Wk3 to WK4
Research Questions | bar: Wk3 to WK4
Research Methods | bar: WK5 to WK8
Research Pipeline | bar: WK6 to WK7
Finalise section in report
Literature Review
Review datasets
Review algorithms
Review evaluation metrics
Finalise section in report
Prototype
Tutorial / Training | bar: Wk2 to WK8
Setup Environment / Code | bar: WK4 to WK8
Create custom dataset
Tweek prototype
Generate evaluation results
Discussion of Results
Write prototype evaluation
Write dataset evaluation
Write hypothesis testing
Write project evaluation
Finalise section in report
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations
Finalise Introduction
Finalise Abstract