## Projected
|  | 22nd Feb | 1st Mar | 8th Mar | 15th Mar | 22nd Mar | 29th Mar | 6th April | 12th Apr | 19th Apr | 26th Apr | 3rd May | 10th May | 17th May | 24th May | 31st May
WP | Task | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15
Report
Create an account | bar: Wk1
Load template | bar: Wk1
Read guidelines | bar: Wk1
Deliverables
Create GIT Account | bar: Wk2
Share with lecturer | bar: Wk2
Commit regularly | bar: Wk3 to Wk15
Record prototype | bar: Wk14
Upload VIVA | bar: Wk14
Submit report | bar: Wk14
Research Methodology
Hypothesis | bar: Wk3 to Wk4
Research Questions | bar: Wk3 to Wk4
Research Methods | bar: Wk4 to Wk7
Research Pipeline | bar: Wk5 to Wk8
Finalise section in report | bar: Wk13 to Wk14
Literature Review
Review datasets | bar: Wk5 to Wk7
Review algorithms | bar: Wk5 to Wk7
Review evaluation metrics | bar: Wk5 to Wk7
Finalise section in report | bar: Wk8 to Wk9
Prototype
Tutorial / Training | bar: Wk2 to Wk9
Setup Environment / Code | bar: Wk3 to Wk9
Create custom dataset | bar: Wk6 to Wk11
Tweek prototype | bar: Wk10 to Wk11
Generate evaluation results | bar: Wk11 to Wk12
Discussion of Results
Write prototype evaluation | bar: Wk12 to Wk13
Write dataset evaluation | bar: Wk12 to Wk13
Write hypothesis testing | bar: Wk13 to Wk14
Write project evaluation | bar: Wk13 to Wk14
Finalise section in report | bar: Wk13 to Wk14
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations | bar: Wk14
Finalise Introduction | bar: Wk14
Finalise Abstract | bar: Wk14

## Actual
|  | 22nd Feb | 1st Mar | 8th Mar | 15th Mar | 22nd Mar | 29th Mar | 6th April | 12th Apr | 19th Apr | 26th Apr | 3rd May | 10th May | 17th May | 24th May | 31st May
WP | Task | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15
Report
Create an account | bar: Wk1 to Wk2
Load template | bar: Wk1 to Wk2
Read guidelines | bar: Wk1 to Wk2
Deliverables
Create GIT Account | bar: Wk2
Share with lecturer | bar: Wk2
Commit regularly | bar: Wk3 to WK10
Record prototype
Upload VIVA
Submit report
Research Methodology
Hypothesis | bar: Wk3 to WK4
Research Questions | bar: Wk3 to WK4
Research Methods | bar: WK5 to WK8
Research Pipeline | bar: WK6 to WK7
Finalise section in report
Literature Review
Review datasets
Review algorithms
Review evaluation metrics
Finalise section in report
Prototype
Tutorial / Training | bar: Wk2 to WK8
Setup Environment / Code | bar: WK4 to WK8
Create custom dataset | bar: WK9 to WK10
Tweek prototype | bar: WK10
Generate evaluation results
Discussion of Results
Write prototype evaluation
Write dataset evaluation
Write hypothesis testing
Write project evaluation
Finalise section in report
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations
Finalise Introduction
Finalise Abstract