## Projected
|  | 22nd Feb | 1st Mar | 8th Mar | 15th Mar | 22nd Mar | 29th Mar | 12th Apr | 19th Apr | 26th Apr | 3rd May | 10th May | 17th May | 24th May | 31st May
WP | Task | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14
Report
Create an account | bar: Wk1
Load template | bar: Wk1
Read guidelines | bar: Wk1
Deliverables
Create GIT Account | bar: Wk2
Share with lecturer | bar: Wk2
Commit regularly | bar: Wk3 to Wk14
Record prototype | bar: Wk13
Upload VIVA | bar: Wk13
Submit report | bar: Wk13
Research Methodology
Hypothesis | bar: Wk3 to Wk4
Research Questions | bar: Wk3 to Wk4
Research Methods | bar: Wk5 to Wk6
Research Pipeline | bar: Wk5 to Wk6
Finalise section in report | bar: Wk12 to Wk13
Literature Review
Review datasets | bar: Wk5 to Wk6
Review algorithms | bar: Wk5 to Wk6
Review evaluation metrics | bar: Wk5 to Wk6
Finalise section in report | bar: Wk7 to Wk8
Prototype
Tutorial | bar: Wk2 to Wk8
Setup Environment, copy code | bar: Wk3 to Wk8
Create custom dataset | bar: Wk5 to Wk10
Tweek prototype | bar: Wk9 to Wk10
Generate evaluation results | bar: Wk10 to Wk11
Discussion of Results
Write prototype evaluation | bar: Wk11 to Wk12
Write dataset evaluation | bar: Wk11 to Wk12
Write hypothesis testing | bar: Wk12 to Wk13
Write project evaluation | bar: Wk12 to Wk13
Finalise section in report | bar: Wk12 to Wk13
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations | bar: Wk13
Finalise Introduction | bar: Wk13
Finalise Abstract | bar: Wk13

## Actual
|  | 22nd Feb | 1st Mar | 8th Mar | 15th Mar | 22nd Mar | 29th Mar | 12th Apr | 19th Apr | 26th Apr | 3rd May | 10th May | 17th May | 24th May | 31st May
WP | Task | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14
Report
Create an account
Load template
Read guidelines
Deliverables
Create GIT Account
Share with lecturer
Commit regularly
Record prototype
Upload VIVA
Submit report
Research Methodology
Hypothesis
Research Questions
Research Methods
Research Pipeline
Finalise section in report
Literature Review
Review datasets
Review algorithms
Review evaluation metrics
Finalise section in report
Prototype
Download Satellite images
Compare images
Create custom dataset
Tweek prototype
Generate evaluation results
Discussion of Results
Write prototype evaluation
Write dataset evaluation
Write hypothesis testing
Write project evaluation
Finalise section in report
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations
Finalise Introduction
Finalise Abstract